## Project Scorecard
PARTIAL FACE RECOGNITION - PROJECT SCORECARD
Objective Score | OBJECTIVE 1: DATASET RESEARCH AND COLLECTION
0.9 | Research and collect a suitable dataset for partial facial recognition.
KR Score | Key Results (Deliverables)
0 | Primary Acquisition: VGGface2 dataset was not found
1 | Secondary Integration: Casia Webface dataset successfully secured (Fully achieved).
0.7 | Supplementary Integration: Incorporation of FEI and LFW datasets for cross-validation (Fully achieved).
Objective Score | OBJECTIVE 2: IMAGE PREPROCESSING AND NORMALISATION
0.7 | Image Preprocessing and normalisation for model readiness.
KR Score | Key Results (Deliverables)
0 | Image alignment before preprocessing. (Cancelled-already aligned)
0.8 | Implementation of normalisation filters to ensure consistent input quality (High progress).
0.6 | Automation of facial occlusion simulation, including masks, scarves, and helmets across the Casia Webface dataset (Full Achieved).
Objective Score | OBJECTIVE 3: PARTIAL FACE RECOGNITION MODEL DEVELOPMENT
0.5 | Creation of a robust Partial Face Recognition Model using advanced Deep Learning.
KR Score | Key Results (Deliverables)
0.6 | Integration of MobileFaceNet architecture; selected for lightweight, resource-efficient processing.
0.4 | Implementation of ArcFace loss function to maximise feature discrimination.
0.6 | Initial performance validation. Current recognition accuracy is 70–75% against the ≥ 85% target.
Objective Score | OBJECTIVE 4: PROTOTYPE AND GUI DELIVERY
0.3 | Deliver a working demonstration of the recognition tool.
KR Score | Key Results (Deliverables)
0.4 | Development of a Streamlit based Graphical User Interface (GUI) wireframe (Started).
0.7 | Real-time identification testing with 5 partial-face test cases (Pending model stability).
Objective Score | OBJECTIVE 5: PROJECT GOVERNANCE AND EFFICIENCY
0.8 | Maintain project documentation and ensure milestone adherence.
KR Score | Key Results (Deliverables)
0.9 | Milestone Adherence: Initiation and Planning phases are 100% satisfied as of Week 08.
0.7 | Documentation Quality: System design and initial findings drafted with zero missing sections.
0.0
1.0
0.6
0.8
0.2