## Sprint
Sprint Plan
Sprint No. | Sprint Goal & Phase | Sprint Tasks | Team Roles Involved | Scrum master | Start Date | End Date | Weekly Standups (Every Friday)
Sprint 1 | Initiation & Scope Baseline | Define Formal Parameters; Assign Roles; Finalize Charter & OKRs. | PM, AI Architect, UI Designer, Doc Lead | Perera | 2025-11-01 | 2025-11-14 | Nov 01 2025 - Signed the Group Contract and assign the team roles¦¦¦¦¦¦¦¦ Nov 07 - Project Intiation (Project Charter, Milestones refining, Budget reports, RACI chart ) | Nov 14 - Other PM Documents review and correct them according to the sope and diliverables
Sprint 2 | Research & Resource Acquisition | Outline Methodologies/ Secure ex; Casia Webface, FEI, and LFW datasets. | PM, AI Architect, Doc Lead | Perera | 2025-11-15 | 2025-11-28 | Nov 21 - According to the tasks research is most important. Discussed who and who research which parts of the project. Select the best research method for the project. Create the Research Mindmap. Ask every mmeber to bring their research ideas. | Nov 28 - Everyone present their ideas on their parts. Dataset and experimental design, Algorithms and core model, Application development and real world challenges, Trainig and performance analysis. According these topics everyone bought some ideas and refine them and discuss the best ideas according to some catogories such as dataset availability, compctness with UI, Linking database, Model architectures. Ask everyone to bring the solitions for alternative dataset as the VGG face2 data set not available. What should we select as out core model to go with our Arc face loss function
Sprint 3 | Data Engineering & Normalization | Implement 112x112 preprocessing workflow/ Automated data splitting (70/15/15). | PM (Dataset Prep), Quality Assurer | Perera | 2025-11-29 | 2025-12-12 | Dec 05 - Last Week Problem - dataset availability. Due to unavailability of the VGG face2 dataset, our team members have found out some datasets like LFW & Casia webface. As per our research we found datasets on kaggle. On this meeting we analysed the 2 dataset and realized that the LFW dataset have less images but casia webface is having more images which is more suitable for project. Then we discussed about the preprocessed approaches which is normalise the images into 112*112. Discussed to split the dataset into three folders as Train, Test and validation. Next week we'll decide to discussed about the errors and bugs. | Dec 12 - What happened with preprocessing?? As we discussed we decided to use casia webface dataset as our dataset and the dataset which was downloaded through the kaggle have already being preprocessed. All the images were images squeezed into 112*112 and normalized. there fore we did not need to align the images and preprocess them. So, perera who is doing the dataset preprocessing part turned into too thin. As per the next just need to splitting the dataset into 3 parts as Train, Test and validation. Next week we'll dicussed the data augmentation
Sprint 4 | Synthetic Augmentation | Develop Gaussian Blur, Colour Jitter, and Structured Occlusion (Masks/Scarves) pipeline. | PM (Dataset Prep), AI Architect | Perera | 2025-12-13 | 2025-12-26 | Dec 19 - What is the data augmentation approach?? As per the research we had two approaches as Offline augmentation and offline augmentation. In this meeting we decided to select the offline data augmentation as most of the facial recognition models were trained under this technique. | Dec 26 - What is the augmentation pipeline?? As we discussed in this meeting we were able to identify the catogories for specially important for the project. The main goal of this one is to prepare the images with partial and low resolution and contrasts. As discussed this part will be transform in the dataset loaders
Sprint 5 | Feature Space Establishment | Define 512-dimensional embedding space; Finalize MobileFaceNet architecture setup. | AI Architect, Quality Assurer | Kasun | 2025-12-27 | 2026-01-09 | Jan 02 - What is our brain of the system?? According to the all members research we decided to use Mobile facenet as our core model. Why the Mobile facenet?? Mobile facenet is more light than other model and it is more compact with the streamlit. As discussed kasun was appointed for the mobile facenet architecture. | Jan 09 - As per the kasun's and perera's Architecture of the mobile facenet , It uses depthwise separable convolutions and inverted residual blocks to drastically reduce computation while keeping high accuracy. The model progressively extracts features through stacked MobileNet‑style blocks, then compresses them into a compact 512‑dimensional embedding. Batch normalization and PReLU activations help stabilize training, and the final normalized embedding is ideal for similarity‑based face matching. Overall, it’s optimized for real‑time facial recognition on mobile or edge devices without sacrificing representational power.
Sprint 6 | Model Training & Loss Optimization | Implement ArcFace Loss; Configure Cosine Annealing learning rate scheduling. | AI Architect, PM | Kasun | 2026-01-10 | 2026-01-23 | Jan 16 - Loss Function Integration - As we agreed before we decided to use Arc face loss function to support the Mobile Facenet. Simply it is a loss function that adds an angular margin to the softmax objective to enforce stronger, more discriminative face embeddings. Then Kasun and perera was assigned to create and overview the arcface loss function and omidu was appointed to advice with the mathematical interpretation. | Jan 23 - On todays meeting members were explain the arcface loss function's code and architecture and how it is align with the mobile facenet. According to Perera's explanation MobileFaceNet generates a 512‑dimensional normalized face embedding, and ArcFace takes this embedding along with the class labels to compute a margin‑enhanced softmax loss. By replacing the standard softmax with ArcFace during training, MobileFaceNet learns features that are more separable in angular space, resulting in higher accuracy and more robust identity discrimination—especially important for partial or challenging face inputs.
Sprint 7 | Performance Validation | Generate ROC Curves and t-SNE visualizations; Verify AUC-ROC score ≥ 0.90. | AI Architect, Quality Assurer | Kasun | 2026-01-24 | 2026-02-06 | Jan 30 - Training the model - Before start to compile the model we needed to import the dataloaders which is train and validation. The training and validation image folders, builds efficient DataLoader pipelines, and then reports how many classes and samples are available in each split. Then each members decided to meet in person to train and explain more each other about the project. | Feb 06- This meeting we had more and more time to discussed about the model training progress. What we discussed?? Is the model overfitted or underfitted. After comparing the results of the model's performance we saw huge overfitting while traininig. So as decided we appointed perara and omidu overview the problem. Then as per our goal of this sprint we discussed what are the validation methods that we can use as well such as ROC Curve, t-SNE embedding plots, Cosine Similarity distributions, verfication and identification.
Sprint 8 | GUI Development & Integration | Build Streamlit-based interface; Integrate static image upload pipeline. | UI Designer, AI Architect, PM | Omidu | 2026-02-07 | 2026-02-20 | Feb 13 - As we had to postpond some validation strategies that we can code, we overviewed the codes and results of the trained model. How is the model performance? Is it performed well witth good accuracy?? Yes we had a good trained model. the project team will convene for a critical Visual Proofing and Statistical Validation session to confirm the model's discriminative power under partial occlusion. The meeting will center on analyzing the ROC Curve and the t-SNE embedding plots generated by the Python evaluation script, with a primary Scrum task for the Quality Assurer to verify that the AUC-ROC score meets the $\geq$ 0.90 success criterion. By examining the Cosine Similarity distributions between same-person and different-person pairs, the AI Architect will demonstrate how the ArcFace Loss and MobileFaceNet architecture have successfully maximized feature separation. This session serves as the formal gateway to the deployment phase, proving through geometric clustering and Top-1 Identification metrics that the system is ready to move from a training environment to the functional Streamlit-based GUI. | Feb 20 - Streamlit design - Omidu took part in design the deployment part with the help of perera on streamlit. As we decided in the first place we decided to streamlit platform for staff attendence system. We decided to sperate the streamlit into 2 parts as registration and recognition. With thoses we'll abale to deploy simple streamlit platform. This part was assigned to omidu with perera.
Sprint 9 | UAT & Accuracy Testing | Execute 5 distinct partial face test scenarios; Achieve accuracy ≥ 85%. | Quality Assurer, UI Designer, PM | Omindu | 2026-02-21 | 2026-03-06 | Feb 27 - Testing - the team will conduct Partial Face Scenario Testing, a pivotal session dedicated to stress-testing the model against real-world biometric challenges. The meeting will focus on the execution of five distinct test scenarios—including surgical masks, winter scarves, hard hats, and side-profile views—to prove the system's resilience when primary facial features are occluded. The Quality Assurer will present detailed test logs to verify an average accuracy of >85%, while the AI Architect analyzes failure cases to ensure the MobileFaceNet embeddings remain consistent despite "noisy" input data. This session directly validates Objective 3, KR 2 of the Project Charter, ensuring the Streamlit GUI maintains its sub-2-second latency and high confidence scores even under the most difficult environmental conditions. | March 06- During this meeting, the Quality Assurer and Project Manager will review the UAT Sheet to confirm that the system successfully delivers on all core functionalities, such as the Streamlit-based interface, the sub-2-second identification latency, and the robust processing of static images. This session is designed to validate that the "Partial Facial Recognition" engine meets the needs of high-traffic sectors like security and healthcare, ensuring the software is not only technically accurate but also user-friendly and reliable for stakeholder evaluation. Successful completion of this meeting serves as the final internal gate before seeking the Project Supervisor's formal audit and sign-off.
Sprint 10 | Documentation & Final Handover | Compile Technical Report and Test Logs; Secure Supervisor Audit Sign-off. | Doc Lead, PM, Quality Assurer | Oishee | 2026-03-07 | 2026-03-20 | Mar 13 - Deployement demonstration - the UI Designer (Omidu) will lead the Streamlit GUI Prototype demonstration, marking the transition from a back-end model to a functional user interface. This meeting focuses on the deployment of a clean, intuitive dashboard that allows users to perform static image uploads for real-time identification. The team will evaluate the interface's layout, ensuring it effectively displays both the uploaded image and the recognition results—including the identified name and the model's confidence score. A critical component of this review is verifying the sub-2-second processing latency required by the Project Charter, ensuring that the integration between the MobileFaceNet engine and the Streamlit framework is optimized for high-traffic operational environments like security checkpoints. | March 20 - The project team will conduct the Supervisor Pre-Audit, a vital quality control milestone where the "Final Project Documentation" package is presented to Dr. Kulvinder Panesar for expert review. This session focuses on securing formal sign-off for the Project Governance & Documentation Excellence objective, ensuring that the Technical Report, User Manual, and Test Logs contain zero missing sections and meet academic standards. The team will present the consolidated evidence of the project’s success, including the AUC-ROC score of ≥ 0.90 and the t-SNE geometric clustering results, to prove that all Key Results (KRs) have been verified. This pre-audit serves as the final validation layer, mitigating the risk of documentation rejection and ensuring that the project is professionally prepared for the ultimate handover and final presentation.
Closure | Post-Sprint Delivery | Prepare and deliver Final Presentation; System walkthrough for stakeholders. | Full Scrum Team | Full team | 2026-03-21 | 2026-04-10 | Mar 27, Apr 03 - the Project Manager and AI Architect will lead the Final Presentation Prep, focusing on synthesizing 18 weeks of technical development into a high-impact slide deck that illustrates the project’s success against its original OKRs. This session involves condensing complex data—such as the ArcFace Loss performance and 85% recognition accuracy—into clear, visual outcomes for stakeholder review. Following this, on April 03, 2026, the team will conduct a Dry Run & Final Handover, performing a complete walkthrough of the live Streamlit GUI demo. This rehearsal is designed to stress-test the live identification process and prepare the full Scrum team for potential stakeholder inquiries, ensuring a seamless transition of the "Partial Facial Recognition" system from a development prototype to a finalized, high-reliability biometric tool. | April 10 - the project reaches its official conclusion with the Project Completion & Sign-off session. This final meeting focuses on Budget Reconciliation, where the Project Manager verifies that all expenditures have remained within the £25,000 baseline and performs a final audit of resource allocations. The team will formally close all project registries, archive the complete Comprehensive Documentation Package, and confirm that all high-level OKRs—from model accuracy to system deployment—have been successfully met and signed off by Dr. Kulvinder Panesar. This milestone marks the formal dissolution of the Scrum team and the transition of the Partial Facial Recognition System from an active development project to a finalized biometric asset, ready for real-world application.

## Backlog
Sprint Backlog
Sprint | Phase & Goal | Task Item | Assigned Roles | Success Metrics / OKRs | Status
1 | Initiation & Scope | Define Formal Parameters & Assign Team Roles | PM, Doc Lead | Signed Group Contract | ✅ Done
|  | Finalize Project Charter & High-Level OKRs | PM, AI Architect | Approved Charter | ✅ Done
2 | Research & Acquisition | Research methodologies (CNN vs SVM) | AI Architect | Research Mindmap | ✅ Done
|  | Secure Datasets (Casia Webface, FEI, LFW) | PM, AI Architect | Dataset availability | ✅ Done
3 | Data Engineering | Implement 112x112 preprocessing workflow | PM (Dataset Prep) | Normalized images | ✅ Done
|  | Automated data splitting (70/15/15) | Quality Assurer | Train/Test/Val sets | ✅ Done
4 | Synthetic Augmentation | Develop Gaussian Blur & Colour Jitter pipeline | AI Architect | Robust training data | ✅ Done
|  | Implement Structured Occlusion (Masks/Scarves) | PM (Dataset Prep) | Partial face samples | ✅ Done
5 | Feature Space | Define 512-dimensional embedding space | AI Architect | Embedding logic | ✅ Done
|  | Finalize MobileFaceNet architecture setup | Quality Assurer | Validated Architecture | ✅ Done
6 | Training & Optimization | Implement ArcFace (Additive Angular Margin Loss) | AI Architect | Feature separation | ✅ Done
|  | Configure Cosine Annealing learning rate | PM | Optimized training | ✅ Done
7 | Performance Validation | Generate ROC Curves and t-SNE visualizations | AI Architect | AUC-ROC ≥ 0.90 | ✅ Done
|  | Verify class separation geometry | Quality Assurer | Geometric clustering | ✅ Done
8 | GUI Integration | Build Streamlit-based interface | UI Designer | Functional GUI | ✅ Done
|  | Integrate static image upload pipeline | AI Architect, PM | Under 2s processing | ✅ Done
9 | UAT & Accuracy Testing | Execute 5 distinct partial face test scenarios | Quality Assurer | Accuracy ≥ 85% | ✅ Done
|  | Identify and fix edge-case bugs | UI Designer, PM | Stable system | ✅ Done
10 | Final Handover | Compile Technical Report & User Manual | Doc Lead, PM | Complete Doc Package | ✅ Done
|  | Secure Supervisor Audit & Sign-off | Quality Assurer | Dr. Panesar Approval | ✅ Done
Closure | Post-Sprint Delivery | Budget Reconciliation (£25,000 baseline) | PM | Financial Audit | ✅ Done
|  | Final Presentation & System Walkthrough | Full Scrum Team | Stakeholder Sign-off | ✅ Done

## P.Backlog
Product Backlog
ID | User Story / Feature | Priority | Acceptance Criteria | Related OKR
PB-01 | Standardized Data Pipeline | Critical | Automated 70/15/15 dataset splitting and 112x112 normalization for Casia Webface, FEI, and LFW datasets. | Objective 1
PB-02 | Synthetic Occlusion Engine | High | Development of an augmentation pipeline featuring Gaussian Blur, Colour Jitter, and Structured Occlusion (masks/scarves). | Objective 1
PB-03 | Core Recognition Architecture | Critical | Implementation of MobileFaceNet architecture optimized for edge-device performance. | Objective 2
PB-04 | Feature Separation Optimization | High | Integration of ArcFace Loss with Cosine Annealing to establish a 512-dimensional embedding space. | Objective 2
PB-05 | Statistical Validation Suite | Medium | Generation of ROC Curves, t-SNE visualizations, and verification of AUC-ROC ≥ 0.90. | Objective 2
PB-06 | Functional Demonstration GUI | High | A Streamlit-based web interface supporting static image uploads and real-time identification results. | Objective 3
PB-07 | System Latency Optimization | Medium | Recognition processing must be completed in under 2 seconds per image. | Objective 3
PB-08 | Biometric Resilience Testing | High | Successful identification in 5 distinct partial face scenarios (eyes-only, surgical masks, scarves, etc.) with ≥ 85% accuracy. | Objective 3
PB-09 | Governance & Compliance | Low | 100% completion of Technical Report, User Manual, and Test Logs for Supervisor sign-off. | Objective 4

## Retrospective
Sprint Retrospective
1. What Went Well? (Successes)
Technical Performance: The system successfully achieved an AUC-ROC score of > 0.90 and a verification accuracy of > 85%, meeting the core SMART objectives.
Architecture Choice: Transitioning to MobileFaceNet proved effective; its depthwise separable convolutions allowed for high accuracy while maintaining the sub-2-second latency required for the Streamlit GUI.
Robustness: The implementation of the ArcFace Loss function successfully maximized feature separation, allowing the model to recognize faces even under "noisy" conditions like masks and scarves.
Documentation & Governance: The team maintained 100% adherence to milestones and secured formal sign-off from Dr. Kulvinder Panesar for the final documentation package.
2. What Could Have Been Improved? (Challenges)
Data Availability: The initial plan to use VGGface2 had to be scrapped due to unavailability, which caused a minor pivot in Sprint 2 and 3 to acquire and analyze Casia Webface instead.
Hardware Constraints: The team faced significant overfitting during the training phase in Sprint 7, requiring intensive manual intervention and code reviews to stabilize the model.
Timeline Pressure: Being restricted to an academic semester (18 weeks) meant that the team had to strictly limit the scope to static images, excluding real-time video integration.
3. Lessons Learned
Agile Flexibility: Breaking the project into two-week sprints allowed the team to catch the VGGface2 data issue early and pivot without delaying the final delivery.
Synthetic Augmentation: Building a custom pipeline for Gaussian Blur and Structured Occlusions was critical; it provided the "proof" needed to satisfy the biometric resilience requirements.
Early Testing: Starting performance validation in Sprint 7 (rather than waiting until the end) was vital for identifying the overfitting issue before the GUI integration phase.
4. Final Project Status
Budget: Final reconciliation confirmed that all expenditures remained within the £25,000 baseline.
Objective Achievement: All four high-level OKRs were met and verified.
Conclusion: The project officially concluded on April 10, 2026, with the dissolution of the Scrum team and the transition of the prototype to a finalized biometric asset.